# Proof-of-Integration Backlog v0.1

משימות הוכחת היתכנות עם תנאי Pass/Fail סגורים

תאריך: 5 ביולי 2026

סטטוס: APPROVED BACKLOG FOR PHASE 1

כל משימת PoI היא Spike מוגבל בזמן. תפקידה להכריע יכולת, ספרייה, Provider או Host. אסור להפוך Spike לקוד Production ללא Review. כישלון אינו נעקף באמצעות הסרת דרישה מחייבת; הוא יוצר ADR לחלופה.

# 1. כללי ביצוע

• Branch נפרד לכל PoI.

• אין שימוש בחשבון Live.

• Secrets אינם נשמרים ב-Git.

• כל PoI מסתיים ב-PASS, FAIL או CONDITIONAL PASS וב-ADR.

• P0 קודם ל-P1.

• Telegram User, WhatsApp User ו-Discord User הם Gates מחייבים; Bot-only אינו Pass.

# 2. מטריצת Backlog

| ID | Priority | Area | Title | Depends | Timebox |
| --- | --- | --- | --- | --- | --- |
| POI-PLAT-ARM-001 | P0 | Platform | ARM64 Docker stack | - | 2 days |
| POI-SEC-SESS-002 | P0 | Security | Encrypted Runtime Session Store | POI-PLAT-ARM-001 | 3 days |
| POI-SOC-WA-USER | P0 | Social | WhatsApp User Adapter | POI-SEC-SESS-002 | 5 days |
| POI-SOC-DC-USER | P0 | Social | Discord User Adapter | POI-SEC-SESS-002 | 5 days |
| POI-SOC-TG-USER | P0 | Social | Telegram User Adapter via TDLib | POI-SEC-SESS-002, POI-PLAT-ARM-001 | 5 days |
| POI-SOC-TG-BOT | P1 | Social | Telegram Bot API supplemental mode | POI-PLAT-ARM-001 | 3 days |
| POI-SOC-TG-COEX | P0 | Social/Data | Telegram User/Bot coexistence and dedup | POI-SOC-TG-USER, POI-SOC-TG-BOT | 2 days |
| POI-MD-001 | P0 | Market Data | Market data provider benchmark | POI-PLAT-ARM-001 | 5 days |
| POI-IBKR-001 | P0 | Broker | IBKR Paper execution | POI-PLAT-ARM-001, POI-MD-001 | 7 days |
| POI-INVPRO-001 | P0 | Source | InvestingPro parser and drift canary | POI-PLAT-ARM-001, POI-SEC-SESS-002 | 5 days |
| POI-NEWS-001 | P0 | News/Filings | Official filings and news ingestion | POI-PLAT-ARM-001 | 5 days |
| POI-TV-001 | P1 | External Signals | TradingView webhook | POI-PLAT-ARM-001 | 2 days |
| POI-AI-001 | P0 | AI | Structured extraction benchmark | - | 5 days |
| POI-EMERG-001 | P0 | Operations | Emergency halt path | POI-PLAT-ARM-001 | 3 days |
| POI-OBS-001 | P1 | Observability | End-to-end telemetry and alerting | POI-PLAT-ARM-001 | 3 days |

## 3.1 POI-PLAT-ARM-001 - ARM64 Docker stack

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Platform |
| Dependencies | None |
| Timebox | 2 days |
| Objective | להוכיח שכל רכיבי הבסיס נבנים ורצים ב-Oracle ARM. |
| PASS | כל images נבנים arm64; services healthy; restart preserves volumes; no privileged containers. |
| FAIL | רכיב ליבה חסר image או דורש emulation בלתי יציבה. |
| Outputs | compose-poi.yaml, image matrix, resource report, decision record |

### Execution steps

• Build Python API/worker image

• Build Node connector/UI image

• Start PostgreSQL, NATS, observability

• Run health and restart tests

## 3.2 POI-SEC-SESS-002 - Encrypted Runtime Session Store

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Security |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 3 days |
| Objective | להוכיח אחסון והחזרת sessions דינמיים ללא חשיפה. |
| PASS | Session survives restart; secrets absent from logs/DB/domain tables; single-session revoke works. |
| FAIL | session plaintext, shared secret scope, or unrecoverable restart. |
| Outputs | session-store spike, threat notes, key rotation test |

### Execution steps

• Encrypt session at rest

• Restart adapter

• Rotate wrapping key

• Revoke one session

• Verify logs redaction

## 3.3 POI-SOC-WA-USER - WhatsApp User Adapter

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Social |
| Dependencies | POI-SEC-SESS-002 |
| Timebox | 5 days |
| Objective | להוכיח קליטה באמצעות חשבון המשתמש כפי שסוכם. |
| PASS | user session works; stable IDs/dedup; allowlist; reconnect; auth-required state; no broker access. |
| FAIL | Bot-only solution, unstable IDs, uncontrolled gaps, or session not securable. |
| Outputs | adapter recommendation, golden fixtures, PoI report, go/no-go |

### Execution steps

• Pair user session

• Allowlist groups

• Capture message/reply/attachment

• Restart/reconnect

• Simulate auth expiry

• Measure gaps and IDs

## 3.4 POI-SOC-DC-USER - Discord User Adapter

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Social |
| Dependencies | POI-SEC-SESS-002 |
| Timebox | 5 days |
| Objective | להוכיח קריאת שרתים/ערוצים/Threads דרך חשבון המשתמש. |
| PASS | user-mode requirements pass; events normalized; resume/dedup reliable; no broker access. |
| FAIL | Bot-only substitution or inability to secure/operate required user mode. |
| Outputs | adapter recommendation, event fixtures, PoI report |

### Execution steps

• Authorize user session

• Allowlist servers/channels

• Capture edits/deletes/threads/attachments

• Restart/resume

• Auth expiry test

## 3.5 POI-SOC-TG-USER - Telegram User Adapter via TDLib

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Social |
| Dependencies | POI-SEC-SESS-002, POI-PLAT-ARM-001 |
| Timebox | 5 days |
| Objective | להוכיח את נתיב החובה והעיקרי דרך חשבון Telegram של המשתמש. |
| PASS | TDLib user flow passes all events, restart, encrypted session, allowlist and health; Bot is not used as substitute. |
| FAIL | only Bot API works, session insecure, or no viable isolated host. |
| Outputs | TDLib adapter spike, host decision, fixtures, PoI report, go/no-go |

### Execution steps

• Obtain api_id/api_hash

• Login by phone/QR/2FA

• List and allowlist chats/channels/topics

• Capture messages/posts/edits/deletes/replies/forwards

• Restart with encrypted TDLib DB

• Re-auth and revoke

• Build/run arm64 or document x86 host fallback

## 3.6 POI-SOC-TG-BOT - Telegram Bot API supplemental mode

| Field | Value |
| --- | --- |
| Priority | P1 |
| Area | Social |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 3 days |
| Objective | להוכיח Bot API כמסלול נוסף לקליטה/התראות. |
| PASS | Bot mode works where authorized; token isolated; no claim of replacing user mode. |
| FAIL | token leakage, duplicate uncontrolled updates, or coupling to user requirement. |
| Outputs | bot adapter spike, permission matrix, notification test |

### Execution steps

• Create dedicated bot

• Test privacy/permissions

• Webhook secret or long polling

• Capture channel/group updates

• Send private test alert

## 3.7 POI-SOC-TG-COEX - Telegram User/Bot coexistence and dedup

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Social/Data |
| Dependencies | POI-SOC-TG-USER, POI-SOC-TG-BOT |
| Timebox | 2 days |
| Objective | להוכיח קליטה מקבילה ללא Candidate כפול. |
| PASS | one canonical evidence/candidate; both observations retained; revisions deterministic. |
| FAIL | double scoring, double candidate or lost provenance. |
| Outputs | dedup algorithm decision, test fixtures, contract examples |

### Execution steps

• Ingest same post via both modes

• Edit/delete from one/both modes

• Verify canonical message and observations

• Run content cluster test

## 3.8 POI-MD-001 - Market data provider benchmark

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Market Data |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 5 days |
| Objective | לבחור primary/fallback ל-quotes, bars, corporate actions and calendar. |
| PASS | field ownership matrix and provider decision satisfy FAST/STANDARD freshness and point-in-time needs. |
| FAIL | missing required fields or no reliable timestamp/fallback. |
| Outputs | benchmark report, field ownership matrix, provider ADR |

### Execution steps

• Benchmark IBKR and external provider

• Measure freshness/completeness

• Validate symbols and timestamps

• Test outage/fallback

• Cost/limits review

## 3.9 POI-IBKR-001 - IBKR Paper execution

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Broker |
| Dependencies | POI-PLAT-ARM-001, POI-MD-001 |
| Timebox | 7 days |
| Objective | להוכיח account, orders, protection, fills and reconciliation in Paper. |
| PASS | no duplicate orders; protection follows fills; normalized events; recovery deterministic; host decision documented. |
| FAIL | blind retry, unprotected fill, unstable gateway or domain leakage of IBKR fields. |
| Outputs | broker adapter spike, capability matrix, host ADR, reconciliation fixtures |

### Execution steps

• Connect TWS/IB Gateway

• Account snapshot

• Instrument mapping

• Limit/stop/bracket

• Partial fill/cancel

• Disconnect/reconnect

• Unknown-state reconciliation

## 3.10 POI-INVPRO-001 - InvestingPro parser and drift canary

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Source |
| Dependencies | POI-PLAT-ARM-001, POI-SEC-SESS-002 |
| Timebox | 5 days |
| Objective | להוכיח login, field extraction, raw snapshot and drift detection. |
| PASS | no silent defaults; schema drift opens circuit; raw snapshots retained; field catalog approved. |
| FAIL | fragile parsing without canary or unverifiable fields. |
| Outputs | parser spike, field catalog, fixtures, drift report |

### Execution steps

• Login/session

• Parse 3-5 page types

• Define field catalog/units

• Golden fixtures

• Break selector to test canary

• Restart session

## 3.11 POI-NEWS-001 - Official filings and news ingestion

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | News/Filings |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 5 days |
| Objective | להוכיח primary-source timestamps, dedup and clustering. |
| PASS | official source path works; point-in-time fields reliable; duplicate headlines cluster. |
| FAIL | timestamp ambiguity or no primary-source verification. |
| Outputs | provider decision, fixtures, timestamp rules |

### Execution steps

• SEC/IR retrieval

• News provider sample

• Published/observed/available timestamps

• Cluster duplicates

• Correction/revision test

## 3.12 POI-TV-001 - TradingView webhook

| Field | Value |
| --- | --- |
| Priority | P1 |
| Area | External Signals |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 2 days |
| Objective | להוכיח authenticated external signal ingestion without direct trading. |
| PASS | alert creates external signal only; duplicates ignored; no broker path. |
| FAIL | direct-to-order or unauthenticated/replayable endpoint. |
| Outputs | webhook contract, security test, fixtures |

### Execution steps

• TLS endpoint

• Secret/idempotency

• Replay/duplicate test

• Payload schema

• Market-data revalidation

## 3.13 POI-AI-001 - Structured extraction benchmark

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | AI |
| Dependencies | None |
| Timebox | 5 days |
| Objective | לבחור model/provider per task and quantify quality/latency/cost. |
| PASS | selected providers meet task thresholds or are restricted to manual/shadow; no self-reported confidence gate. |
| FAIL | unreliable structured output or unbounded prompt/tool behavior. |
| Outputs | benchmark report, provider matrix, prompt/model versions, golden set |

### Execution steps

• Build golden set

• Test entity/instruction/catalyst/critic

• Schema validation

• Adversarial prompts

• Latency/cost comparison

• Calibration assessment

## 3.14 POI-EMERG-001 - Emergency halt path

| Field | Value |
| --- | --- |
| Priority | P0 |
| Area | Operations |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 3 days |
| Objective | להוכיח GLOBAL_ENTRY_HALT עצמאי מה-UI וה-AI. |
| PASS | queued/new entries blocked; protective exits remain; state survives restart; full audit. |
| FAIL | order submits after halt or protection is cancelled. |
| Outputs | runbook, drill evidence, test automation |

### Execution steps

• Set halt via UI

• Set halt via emergency endpoint/CLI

• Queue order then halt

• Verify pre-submit check

• Restart services

• Resume with MFA/reconcile

## 3.15 POI-OBS-001 - End-to-end telemetry and alerting

| Field | Value |
| --- | --- |
| Priority | P1 |
| Area | Observability |
| Dependencies | POI-PLAT-ARM-001 |
| Timebox | 3 days |
| Objective | להוכיח tracing, metrics, logs and notification routing. |
| PASS | correlation ID end-to-end; no secrets; alerts dedup/escalate; health visible. |
| FAIL | missing trace across boundary or secret exposure. |
| Outputs | dashboards, alert rules, redaction tests |

### Execution steps

• Trace source-to-decision

• Redact secrets

• Create critical alerts

• Send Telegram private alert

• Simulate adapter down/data stale

# 4. Exit Gate

Phase 2 Production implementation may begin only when every P0 PoI is PASS or an approved ADR supplies an equivalent implementation path. POI-SOC-TG-USER cannot be satisfied by POI-SOC-TG-BOT.